## Slide 1: Planning Your Next 4 Months
Hillary Kane
Coordinated Campaign Committee
August 5, 2016

## Slide 2
Notes: There are 14 weeks until Election Day!!!

## Slide 3: Backwards Planning
November 8th
November 4th-7th
October 24th-November 3rd
October
September
August

## Slide 4: November 8th
# Polling places covered
  Volunteers
  Literature
  Signage
  T-shirts
Candidate escort
Sound car
Phone calling/Door knocking
Election Night Party

## Slide 5: November 4th-7th
GOTV
  Reminding your likely supporters to vote
  No longer about selling your candidate – instead its about motivating those already on your side
  Final lit drop/phone banking of 4’s & 5’s
Distribution of materials and instructions to Election Day volunteers
Prep press releases
Candidate in high visibility events

## Slide 6: Final Days Calendar
Saturday, November 5 – Final canvassing of likely voters; candidate visibility events
Sunday, November 6 – Final canvassing of likely voters; distribution of materials to poll workers
Monday, November 7 – Phone banking of likely voters; social media campaign; distribution of materials to poll workers

## Slide 7: October 24th-November 3rd
Realistic assessment of voter targeting
Plan on final expenditures of $$
Final call for GOTV and Election Day volunteers
Design final literature; get printed
Notes: Note – people who care about specific issues but may not have Green candidate in their location

## Slide 8: October
Ongoing outreach driven by voter targeting
  Door knocking, phone banking, social media
Press releases
Debates
GOTV planning
Radio ads
FUNDRAISING
Promotional material
Notes: Announce four issues

## Slide 9: September
Ongoing outreach driven by voter targeting
  Door knocking, phone banking, social media
Press releases
House parties, honk & waves, farmer’s markets, Labor Day parade
Volunteer recruitment
FUNDRAISING
Promotional material
Campaign office?

## Slide 10: August
Ongoing outreach
  Door knocking, phone banking, social media
Press releases – statements on incumbent, current events, etc
Ballot access?
House parties, block parties, honk & waves, Gay Pride parade
Volunteer recruitment
Voter targeting analysis
FUNDRAISING

## Slide 11: Action Planning
Choose ONE thing
  Press
  Volunteer recruitment
  GOTV
  Literature/Signage
  Events & publicity
  Fundraising
Make a plan – who, how, by when